## Sheet1
Epic | Priority | User stories | Acceptance Criteria (CheckList) | Story Point(Time Estimate) | Status | Other labels | Story No
Student user | High | As a Student, I will be able to login with student id and password provided by the admin so that I can use the payment feature in the herald college website. | Student should be able to login with his provided student id and password and show the payment feature he can use. | 4 days | To Do | Herald college website | 1
| High | As a Student, I will be able to check the payment details of the enrolled course and level so that I don't have to call the finance department time again to know about actual fees. | Student should be able to see his payment details providing his student id, student name, enrolled course and level and total fees. | 5 days | To Do | Herald college website | 2
| High | Student payment info should be renewed after every semester. | In Herald database, after completion of semester student information of Payment should be updated to UNPAID. | 6 days | To Do | connect IPS website | 3
Connect IPS User | High | As a student, I will be able ta make online payment via ConnectIPS website. | When student clicks on pay fees button it should redirect to connectIPS website. | 3 days | To Do | connect IPS website | 4
| High | As a connectIPS user, I will be able to credit Herald college bank account in which fees is already mentioned with student ID. | When connectIPS user makes the final payment it will debit the users account balance and credit the herald college bank account. | 4 days | To Do | Herald college website | 5
| High | After the successful payment, connect IPS database and herald database communicate with each other and update the particular studentID payment status as PAID. | In Herald database, after the successful transaction student information of Payment should be updated to PAID. | 6 days | To Do | connect IPS website | 6
Payment Management | High | As a student or parent, I want to have access of payment receipt that has transaction ID, Student ID and status getway of the payment which can be downloaded from Connect IPS website | Receipt of payment must be generated immediately after the payment is done successfully with transaction ID, payment status and Student ID. The receipt must be made downloadable with the file format of PDF. Receipt must contain only the details of student, parent who make payment. | 3 days | To Do | connect IPS website | 7
| High | As a student or parent, I want to have access of payment receipt that has transaction ID, Student ID and status getway of the payment which can be downloaded from Connect IPS website | Payment status should be displayed properly and immediately after the successful payment. Payment status must have 3 things, "paid" if the payment is done, "unpaid" if the payment is hald or not done and access should be given access to either student or teacher once the payment is done successfully.ID, payment status and Student ID. The receipt must be made downloadable with the file format of PDF. Receipt must contain only the details of student, parent who make payment. | 4 days | To Do | Herald college website | 8